## New Task Find
Sr.No | Task | Days | Status
| Multiple Branch Create | 10.25
| We will create model_branch in database to handle the multiple branch | 1.25
| We will creating the UI designee to view the child branch from super-admin and restaurant dashboard. | 1
| Bind & Populate data to the child branch from super-admin and restaurant dashboard | 1.5
| We will creating the UI designer to add/edit/delete/ child branch from super-admin and resturant. | 1
| We will implement the validation to child branch from client and server side | 0.5
| We will implement the functionality to add/edit/delete/ child branch from Super-Admin and resturant. | 1.75
| We will implement the logic to will hand over the parent branch to the child branch in the model_branch | 0.75
| Can we give a dropdown of multiple branches on each model on the restaurant admin dashboard? |  | Discussion
| Can handle all modules of multiple branches with one credential. | 2.5
| Merging multiple branches and changing teams to work from one branch into another branch. such as: 1. Waiter -> Parent branch to Child branch. 2. User 3. Admin 4. Manager |  | Discussion
| If add the any one item in parent branch so we can show the item in multiple branch from restaurant admin. Option.1: we can generate the item excel file from the parent branch then import in child branch. Option.2: we can move the item from one branch into another branch from restaurant admin. |  | Discussion
| After setting up a restaurant branch, it is necessary to make payment first to get approval from the super-admin. i. Implement the functionality to payment. ii. Create the migration to manage of approval payment history. iii. Creating UI Design to Show Approval Branch Payment History from super-admin and restaurant dashboard. iv. Bind & Populate data to the child branch from super-admin and restaurant dashboard. |  | Discussion
| Note: - (discussion) If a branch is created from the restaurant administrator, then the super-admin will approve on his behalf and only after the approval, he will be able to use the child branch. OR super-Admin will add to child branch to the restaurant and edit, the restaurant will not add its branch. |  | Discussion
| Tax Management | 9.25
From the restaurant dashboard
| Change UI design of Tax | 0.5
| Modifying the migration file | 0.25
| Write logic to automatically generate a new row when adding taxes | 0.75
| Write the logic, double-click the row, and then update the column value | 0.75
| Implement validation and error handling from server and client side | 0.25
| Write logic to save and delete from the restaurant | 0.5
| Implement functionality to fetch and bind data from DB | 0.5
| From the Super-Admin Dashboard |  | Discussion
| Create UI design of tax type list and add form | 0.75
| Create a migration file to handle the database | 0.25
| Implement validation and error handling from server and client side | 0.5
| Write the logic for saving and deleting from the server side | 0.75
| Implement add/edit/update functionality | 0.75
| Implement functionality to fetch and bind data from DB | 0.5
| Assign tax type to restaurant from super-admin dashboard | 1
| Create the API to show the tip-percentage from POS or Mobile | 1.25
| Tip percentage | 2.75
| Create a migration file to handle the database | 0.25
| We will creating the UI designee to view the tip-percentage from restaurant dashboard | 0.25
| Bind & Populate data to the tip percentage | 0.5
| We will create the UI designee to add/edit/delete to tip-percentage | 0.25
| We will implement the validation to tip-percentage from client and server side | 0.25
| We will implement add/edit/delete functionality to tip-percentage | 0.5
| We will create the API to show the tip-percentage from POS or tablet | 0.5
| Testing And Error Handling. | 0.25
| Option of Reservation | 6.25
| Restaurant type booking. Please check the suggestion point below. Then give us suggestions. Such as: i. Phone: Customers can call the restaurant directly to make a reservation over the phone. ii. Online: Many restaurants allow customers to make reservations online through their website or a third-party reservation platform. iii. Walk-in: Some restaurants do not accept reservations and operate on a first-come, first-served basis |  | Discussion
| We will creating reservation in database to handle the reservation with payment | 0.5
| We will creating the UI designee to view the reservation from restaurant dashboard | 0.75
| Bind & Populate data to the Option of Reservation. | 1
| We will implement the validation to reservation from client and server side | 0.5
| We will implement add/edit/delete functionality to reservation | 1.25
| We will create the API to show the reservation from POS or tablet | 1
| Required the reservation form. Such as: Name, Email, Phone, Date Time, Number of Guests, Special Requests (TextArea). Discuss Point: - Number of Guests OR according to the table OR full restaurant booking |  | Discussion
| Reservation confirmation then send the email to vendor or supplier | 1.25
| Payment process with the debit or credit card |  | Discussion
| Handle the reservation status if payment success then show the booking from vendor and supplier dashboard or email confirmation. |  | Discussion
| Handle the reservation payment status, save the payment response |  | Discussion
| Create the UI designed to show the payment history |  | Discussion
| Bind & Populate data to the payment history |  | Discussion
| Special item & Cash In/Out | 8.25
Open Price Item Buttons
| Create UI design of Open Price Item Buttons list. | 0.5
| Create a migration file to handle the database. | 0.25
| Bind & Populate data to the Open Price Item Buttons. | 1.25
| Write logic to automatically generate a new row when adding Open Price Item Buttons. | 1
| Write the logic, double-click the row, and then update the column value. | 1.25
| Implement validation and error handling from server and client side. | 0.5
| Write the logic for saving and deleting from the server side. | 0.75
| Implement functionality to fetch and bind data from DB. | 0.5
| Testing And Error handleing | 0.25
Payment Item Button
Negative Prices
Cash In/Out
| Create UI design of Cash In/Out list. | 0.5
| Create a migration file to handle the database. | 0.25
| Bind & Populate data to the Cash In/Out. | 0.5
| Implement validation and error handling from server and client side. | 0.25
| Implement functionality to fetch and bind data from DB. | 0.25
| Testing And Error handleing | 0.25
| Extra Fee | 3.75
| Create UI design of extra Fee list. | 0.5
| Create a migration file to handle the database. | 0.5
| Bind & Populate data to the Extra Fees. | 0.5
| Write logic to automatically generate a new row when adding Extra Fees. | 0.5
| Write the logic, double-click the row, and then update the column value. | 0.5
| Implement validation and error handling from server and client side. | 0.25
| Write the logic for saving and deleting from the server side. | 0.5
| Implement functionality to fetch and bind data from DB. | 0.25
| Testing And Error handleing | 0.25