## 15-january-2024
Sr.No | Task | Task ensure | Status | Work Progress | Comment
Here are the requirements that we have for the new POS. All these factors are important to us and have been collected after years of being in the business
1 | POS for small and large retail stores, small and large corporate restaurants, bars, pizza, and all involved | Both | Understanding | Completed
2 | Automatically integrate with UBER EATS and DOOR DASH, GRUB HUG, and find a way for these companies to pay us for giving them access | Both | Understanding | Completed
3 | When an ISO wants to integrate, find a way for them to leave us some residual profit | Both | Discussion | Pending
4 | Have the option of reservation and accept payments to cover a debt (Layaways) | Both | Discussion | Working
5 | Create a customizable map of tables based on preferences and needs. | Both | Discussion | Pending
6 | Label the tables and chairs with letters from A to Z, starting from the left | Both | Discussion | Pending
7 | Display the name of the waiter on the ticket at the table. | Both | Discussion | Pending
8 | Include item types in the menu for accounting control | Mobile Team | Understanding
9 | Explore options for customers to order from their table and consider adding cost-based games to benefit from it. Table Ordering Tablet like (Ziosk). But the most important part is let the kids play with a charge $$. https://en.wikipedia.org/wiki/Ziosk. | Both | Understanding | Pending
10 | Completely D….. tickets after viewing them, like ALDELO. | Both | Discussion | Pending
11 | Ensure PCI compliance. | Both | Discussion | Pending
12 | Open bar tabs and easily find them using the name or card. | Both | Discussion | Pending
13 | Include the option to display the time when the order was sent on the ticket, and the manager can see it on their phone or tablets. | Both | Understanding | Pending
14 | Display the suggested tip percentage and total $ amount on the receipt for customer convenience. | Both | Understanding | Working
15 | Designate a specific station as the cash register for cash payments. | Both | Discussion | Pending
16 | Keep the cashier within the system and menu to save steps. | Both | Discussion | Pending
17 | Add a button to order items not found in the menu, categorized by department (Miscellaneous, Bar Miscellaneous, Party Pack, Gift Card, etc. | Both | No Understanding | Pending
18 | Implement a cash discount option, controlled, and authorized by us only. Customers who decline the cash discount should not have the option to enable it | Both | Discussion | Pending
19 | Allow transferring of tickets to other waiters with and/or without manager authorization | Both | Understanding | Pending
20 | Change table locations with or without manager authorization | Both | Understanding | Pending
21 | Option for waiters to not be able to clock out until they have closed all their tables | Both | Understanding | Pending
22 | Each waiter can act as their own bank, and the report shows how much cash they have on hand. If they have received tips, it should be deducted from that amount. They should also be able to cash out the money they have collected to pay their tips. | Both | Discussion | Pending
23 | When waiters finish their shift, they have the option to report their tips. The manager can set a minimum tip requirement (e.g., 15%) or prevent them from leaving. | Both | Discussion | Pending
24 | When reporting tips, waiters can allocate a certain percentage to assistants, bartenders, etc., and the system will apply that percentage to distribute the money, accordingly, notifying the recipients where the money comes from. These tips should be automatically reported on the paycheck. | Both | No Understanding | Pending
25 | Is it possible to edit the batch and settlement of card transactions after they have been sent to the bank? Can there be a grace period in the system to pause the sending of settlements to the bank for a certain time (e.g., 1 hours) to allow for tip editing? | Both | Not Understanding | Pending
26 | Waiters should have access to view their sales and tips with the appropriate permissions | Both | Understanding | After Completed
27 | Practice mode should be available for training purposes, but the results should not be reported as actual sales. Managers should be able to review the practice sessions. | Both | Discussion | Pending
28 | The POS system should nidificate and print the ticket when the kitchen or bar printer is not functioning. | Mobile Team
29 | When the keyboard opens, the keys should be large and easy to press | Mobile Team
30 | Ticket Notes should be included on the bottom of the ticket for the cook to see it. | Both | No Understanding | Pending
31 | The option to have sequential or random ticket numbers | Both | Understanding | Completed
32 | Employee codes should be hidden in the employees file, and if lost, they can be recovered with manager approval | Both | Understanding | Working
33 | When adding a new employee, all necessary folders should be created, including the Liquor License Certificate | Both | Understanding | Before Working | When add new resurant
34 | Employees can log in using fingerprint, code, cards, or other methods | Both | Discussion | Pending
35 | Waiters should only be able to access the system after clocking in, Optional | Both | Discussion | After Working
36 | Easy copy and paste menus from other POS to our POS | Both | Discussion | Pending
37 | Integrated QR code generator | Both | Discussion | Pending | Type of generate QR code
38 | Table-specific QR codes to see the menu and ordering | Both | No Understanding | Pending
39 | Ability to resend items to the kitchen and bar | Both | Understanding | Pending
40 | Ability to reorder a round or anything previous order by just clicking the item in the ticket | Both | Understanding | Pending
41 | When it comes time to pay, multiple payment methods should be accepted, including multiple cards for a single ticket (Credit Cards, Gift cards, Cash, Crypto, or any other). | Both | Discussion | Pending
42 | Any changes made to the menu should automatically update across all businesses within the corporation (When they have multiple locations) | Both | No Understanding | Pending | evary branch as separate restaurant
43 | Create an app with all the necessary reports and tools for the owner to manage from their phone or tablet | Both | Discussion | Pending
44 | Develop a guest app that displays order history and enables customers to pay by scanning the ticket without handing their card to the server (like Heartland POS). https://youtu.be/LeVVXV5--Z0?si=jLaajOtqwrGlvunI | Both | Understanding | Pending
45 | Be able to see all the used tables and when every single order is placed live. | Both | Discussion | Pending
46 | Look for the way to load the tips onto prepaid cards for employees. | Both | Discussion | Pending
47 | Integration with QuickBooks | Both | No Understanding | Pending
Inventory
| Full control of Inventory. | Both | Understanding | Completed
https://youtu.be/2KMH1uMXPjc?si=McKe5603p09ochJC
https://youtu.be/iVOYex9NWDo?si=X1UO8I8SkjWeqEGm
Reports
48 | Employee payments are biweekly (26 weeks), but some companies want to pay weekly (52 weeks). | Both | No Understanding | Pending
49 | Automatically deduct the cash when tips are paid (Like Aloha). | Both | Discussion | Pending
50 | Schedule where employees can choose and exchange their shifts with others, with managers approved or manager knowledge. | Both | Discussion | Pending
51 | Price change reports. | Both | Understanding | Pending
52 | Keep a history Log and who did it: when someone do a Void, Discount, Price Change, or any other important thing that the owner would like to know. | Both | Discussion | Pending
53 | Display sales reports in the form of graphs for viewing on mobile devices or the web (SpotON). They have 77 available report options. I LIKE THESE REPORTS | Both | Discussion | Pending
Notifications
54 | Send the corresponding notifications to the owner or manager: Voids, Comps, Discounts, Cancellations, etc. by Email, Pdf, text, Excel, etc. | Web Team | Understanding | Pending
55 | Ability to send messages within the group, either individually or all entire group. | Both | Understanding | Working
To-Go Orders/Pizzas
56 | Have the option to input customer information to save their data and be able to access their order history. | Both | Understanding | Pending
57 | Know what the customer has ordered or determine what type of customer they are | Both | Understanding | Pending
58 | If we offer delivery, be able to view the map and track the driver's location | Both | Understanding | Pending
59 | Have a field to enter the driver's license for the driver | Both | Understanding | Pending
60 | Calculate the distance in miles to be able to charge per mile driven | Both | Understanding | Pending
61 | For online orders, automatically update the prices from the local menu, and when orders are placed, print a notification at the cash register and direct to the kitchen | Both | Understanding | Pending
Waiter sending orders
62 | Keep the main page as clean as possible, activating only the necessary elements when buttons are pressed | Both | No Understanding | Pending
63 | Have the option to Send and Stay to continuing with the order. For example, if the customer wants appetizers quickly, they can send those items immediately while continuing to add to the order | Both | No Understanding | Pending
64 | Make the ordering process for servers as simple as possible, minimizing the need for them to leave and re-enter the order | Both | Discussion | Pending
65 | Allow customization of quantities for specific items when ordering. For example, if someone orders tacos, they can specify the quantity of beef, chicken, pork, etc. they want. | Both | Understanding | Pending
66 | Enable unlimited splitting of the ticket | Both | Understanding | Pending
67 | When splitting the ticket, keep all the tickets on the same screen and make them available for adding or removing items. | Both | Discussion | Pending
68 | Provide the option to split the bill within the same ticket, and if desired, view the split amounts in separate tickets without leaving the screen (like "Manage Table" feature in SpotON) | Both | Discussion | Pending
69 | Allow splitting of a single item and assigning it to multiple individuals. | Both | Discussion | Pending
70 | Repeat an entire round of orders with a single button press | Both | Discussion | Pending
71 | Include a search button on the menu interface for faster product lookup if the user is unsure of its location (this will display multiple options with prices and locations and can be selected from there). | Both | Discussion | Pending
72 | Use a "MOD" button with options such as "NO," "LIGHT," "ADD," "EXTRA," "INSIDE," and "ADD Mode" for modifications. For example, if the menu item is "Chicken," pressing "NO" will display "NO Chicken" Add or Extra may need to be with extra charge. | Both | Discussion | Pending
73 | Offer multi-column modifiers, where all modification options are listed in separate columns for easier selection (similar to Future POS). https://youtu.be/vSqT22b19Dk?si=Awy26zC1scBQG-0C | Both | No Understanding | Pending
74 | Provide a notes section for the kitchen to include specific instructions for an order. | Both | Understanding | Pending
75 | When ordering a product with modifications or additions that incur additional charges, have the option to calculate and display the total cost of the main product. For example, 1 Margarita for $10 with Patrón for $5 (in small font and/or possibly removing this price) Total show as Margarita $15. | Both | No Understanding | Pending
76 | Allow each server to have their own cash bank, generate reports, and reconcile their cash at the end of their shift. | Both | Discussion | Pending
77 | Support dual pricing, like the HotSauce system | Both | No Understanding | Pending
78 | Integrate Caller ID for takeout orders this way you know the customer’s name | Both | Discussion | Pending
79 | Handle cases where a customer may have multiple phone numbers or a single phone number is used by multiple customers, ensuring the system can associate the correct data with the corresponding customer (e.g., schools with shared phone numbers). | Both | Discussion | Pending
Cashier
80 | Place a button upfront for applying discounts, and within that button, include options such as Tax Exempt (with the ability to enter the Tax-Exempt number), Employee discounts, Police discounts, Coupons, etc. The discount amount should be visible before applying it to the ticket and there should also be an option to remove the discount. | Both | Understanding | Progress
81 | When customers want to pay using multiple payment options (Cash, Credit Card, Gift Card, etc.), ensure a seamless process that allows them to split the payment as desired, while keeping the ticket open without any issues | Both | Understanding | Progress
82 | Enable cash register opening without requiring a sale | Both | No Understanding | Pending
83 | Offer the ability to send receipts to customers via email, text, etc. | Both | Understanding | Pending
84 | Provide the capability to give credit to a customer, whether it's through a Credit Card, Cash, or Gift Card. | Both | Understanding | Pending
85 | Allow voiding of credit card payments but keep track of who did it. | Both | Understanding | Pending
86 | Enable partial credit to be applied to a credit card account that has already been paid. | Both | No Understanding | Pending
87 | Is it possible to integrate a camera that can instantly communicate with the POS system? | Both | Understanding | Mandatory
88 | Can cryptocurrency integration be implemented? | Both | Understanding | Certainly! Cryptocurrency integration with POS
89 | Support both physical and electronic gift cards, allowing for immediate or birthday-specific delivery. | Both | Discussion | Pending
90 | Set a maximum discount limit based on the employee's level within the system. | Both | Discussion | Pending
91 | Ensure that the Cash Discount ticket, when printed from the Credit Card Machine, clearly indicates the amount paid by the customer.
Making the menu
92 | Allow copying or cloning of items, modifiers, or force modifiers, and then rename the new product as desired.
93 | When the price of a modifier is changed, automatically update the price of the corresponding force modifier.
94 | Provide the option to add photos of dishes or drinks. (Create a folder and make it accessible for basic items: beer caps, sodas, juices, vegetables, fruits, etc.)
95 | Schedule events: Enable the creation of events throughout the year and make it easy to set the date and time for special events, holidays, and control labor cost (as seen in SpotON).
Setting up the system:
96 | Set up printers from the server without having to configure them on each POS individually.
97 | Have the "?" or Help button prominently displayed or easily accessible, allowing users to check for internet connectivity and providing quick access for customers to provide tools for tech support.
98 | Pre-install the drivers for the printers that will be used.
99 | Pre-install the POS software to our hardware.
100 | Pre-install TeamViewer and AnyDesk or other remote access software to our hardware.
101 | Make the printer installation process user-friendly and easy.
102 | Make the integration of PAX or any other devices straightforward.
103 | Set up PAX or any other devices with First Data and/or Tsys.
104 | Restrict actions and changes without approval from the designated authority.
105 | Perform updates periodically and assess the impact on clients' current settings before deciding to proceed, ensuring that the updates do not disrupt their existing configurations.

## POS-System
Sr.No | Task | Days | Status
| Multiple Branch Create | 10.25
| We will create model_branch in database to handle the multiple branch | 1.25
| We will creating the UI designee to view the child branch from super-admin and restaurant dashboard. | 1
| Bind & Populate data to the child branch from super-admin and restaurant dashboard | 1.5
| We will creating the UI designer to add/edit/delete/ child branch from super-admin and resturant. | 1
| We will implement the validation to child branch from client and server side | 0.5
| We will implement the functionality to add/edit/delete/ child branch from Super-Admin and resturant. | 1.75
| We will implement the logic to will hand over the parent branch to the child branch in the model_branch | 0.75
| Can we give a dropdown of multiple branches on each model on the restaurant admin dashboard? |  | Discussion
| Can handle all modules of multiple branches with one credential. | 2.5
| Merging multiple branches and changing teams to work from one branch into another branch. such as: 1. Waiter -> Parent branch to Child branch. 2. User 3. Admin 4. Manager |  | Discussion
| If add the any one item in parent branch so we can show the item in multiple branch from restaurant admin. Option.1: we can generate the item excel file from the parent branch then import in child branch. Option.2: we can move the item from one branch into another branch from restaurant admin. |  | Discussion
| After setting up a restaurant branch, it is necessary to make payment first to get approval from the super-admin. i. Implement the functionality to payment. ii. Create the migration to manage of approval payment history. iii. Creating UI Design to Show Approval Branch Payment History from super-admin and restaurant dashboard. iv. Bind & Populate data to the child branch from super-admin and restaurant dashboard. |  | Discussion
| Note: - (discussion) If a branch is created from the restaurant administrator, then the super-admin will approve on his behalf and only after the approval, he will be able to use the child branch. OR super-Admin will add to child branch to the restaurant and edit, the restaurant will not add its branch. |  | Discussion
| Tax Management | 9.25
From the restaurant dashboard
| Change UI design of Tax | 0.5
| Modifying the migration file | 0.25
| Write logic to automatically generate a new row when adding taxes | 0.75
| Write the logic, double-click the row, and then update the column value | 0.75
| Implement validation and error handling from server and client side | 0.25
| Write logic to save and delete from the restaurant | 0.5
| Implement functionality to fetch and bind data from DB | 0.5
| From the Super-Admin Dashboard |  | Discussion
| Create UI design of tax type list and add form | 0.75
| Create a migration file to handle the database | 0.25
| Implement validation and error handling from server and client side | 0.5
| Write the logic for saving and deleting from the server side | 0.75
| Implement add/edit/update functionality | 0.75
| Implement functionality to fetch and bind data from DB | 0.5
| Assign tax type to restaurant from super-admin dashboard | 1
| Create the API to show the tip-percentage from POS or Mobile | 1.25
| Tip percentage | 2.75
| Create a migration file to handle the database | 0.25
| We will creating the UI designee to view the tip-percentage from restaurant dashboard | 0.25
| Bind & Populate data to the tip percentage | 0.5
| We will create the UI designee to add/edit/delete to tip-percentage | 0.25
| We will implement the validation to tip-percentage from client and server side | 0.25
| We will implement add/edit/delete functionality to tip-percentage | 0.5
| We will create the API to show the tip-percentage from POS or tablet | 0.5
| Testing And Error Handling. | 0.25
| Option of Reservation | 79
| Restaurant type booking. Please check the suggestion point below. Then give us suggestions. Such as: i. Phone: Customers can call the restaurant directly to make a reservation over the phone. ii. Online: Many restaurants allow customers to make reservations online through their website or a third-party reservation platform. iii. Walk-in: Some restaurants do not accept reservations and operate on a first-come, first-served basis |  | Discussion
Reservation
| Create a migration file to handle the database. | 1
| Creating the UI design to view the reservation from restaurant dashboard. | 1.5
| Bind & Populate data to the reseravation booking. | 1.75
| create the UI designe to add/edit/delete to reservation. | 1.5
| implement the validation to reservation from client and server side. | 1
| implement add/edit/delete functionality to reservation. | 2
| Create the UI to booking list and bind & populate data. | 1
| Testing And Error Handling. | 0.25
Reservation Payment
| Create a migration file to handle the database. | 0.5
| Creating the UI design to view the reservation payment from restaurant dashboard. | 1
| Bind & Populate data to the reseravation payment | 1.5
| create the UI designe to add/edit/delete to reservation payment. | 1.75
| implement the validation to reservation payment from client and server side. | 0.5
| implement add/edit/delete functionality to reservation payment. | 1.5
| Create the UI to payment booking list and bind & populate data. | 1
| Testing And Error Handling. | 0.5
Reservation Booking
| Create a migration file to handle the database. | 0.75
| Creating the UI design to view the reservation Booking from restaurant dashboard. | 1.5
| Bind & Populate data to the reseravation Booking | 1
| create the UI designee to add/edit/delete to reservation Booking | 1.75
| implement the validation to reservation Booking from client and server side. | 0.5
| implement add/edit/delete functionality to reservation Booking. | 1.25
| Testing And Error Handling. | 0.5
Restaurant Booking
| Create a migration file to handle the database. | 0.75
| Creating the UI design to view the Restaurant Booking from restaurant dashboard. | 1
| Bind & Populate data to the Restaurant Booking. | 0.75
| create the UI designee to add/edit/delete to Restaurant Booking. | 1.5
| implement the validation to Restaurant Booking from client and server side. | 1
| implement add/edit/delete functionality to Restaurant Booking. | 1.75
| Create the UI to Restaurant Booking list and bind & populate data. | 1
| Testing And Error Handling. | 0.25
Email/SMS Template
| Create a migration file to handle the database. | 1
| Creating the UI design to view the Email/SMS Template from restaurant dashboard. | 1.5
| Bind & Populate data to the Email/SMS Template. | 0.75
| create the UI designee to add/edit/delete to Email/SMS Template. | 1
| implement the validation to Email/SMS Template from client and server side. | 1
| implement add/edit/delete functionality to Email/SMS Template. | 2
| Create the UI to Email/SMS Template list and bind & populate data. | 1
| Testing And Error Handling. | 0.5
| Implement the editor to email/sms | 1
Booking Schedule Option
| Create a migration file to handle the database. | 0.5
| Creating the UI design to view the reservation setting from restaurant dashboard. | 2.5
| Bind & Populate data to the reseravation setting | 1.5
| create the UI design to add/edit/delete to reservation setting. | 2
| implement the validation to reservation setting from client and server side. | 0.75
| implement add/edit/delete functionality to reservation setting. | 1
| Create the UI to setting booking date list and time and bind & populate data. | 5
| Testing And Error Handling. | 0.5
| We will creating reservation in database to handle the reservation with payment | 0.5
| We will creating the UI designee to view the reservation from restaurant dashboard | 0.75
| Bind & Populate data to the Option of Reservation. | 1
| We will implement the validation to reservation from client and server side | 0.5
| We will implement add/edit/delete functionality to reservation | 1.25
| We will create the API to show the reservation from POS or tablet | 1
| Required the reservation form. Such as: Name, Email, Phone, Date Time, Number of Guests, Special Requests (TextArea). Discuss Point: - Number of Guests OR according to the table OR full restaurant booking |  | Discussion
| Reservation confirmation then send the email to vendor or supplier | 1.25
| Payment process with the debit or credit card |  | Discussion
| Handle the reservation status if payment success then show the booking from vendor and supplier dashboard or email confirmation. |  | Discussion
| Handle the reservation payment status, save the payment response |  | Discussion
| Create the UI designed to show the payment history |  | Discussion
| Bind & Populate data to the payment history |  | Discussion
| Special item & Cash In/Out | 8.25
Open Price Item Buttons
| Create UI design of Open Price Item Buttons list. | 0.5
| Create a migration file to handle the database. | 0.25
| Bind & Populate data to the Open Price Item Buttons. | 1.25
| Write logic to automatically generate a new row when adding Open Price Item Buttons. | 1
| Write the logic, double-click the row, and then update the column value. | 1.25
| Implement validation and error handling from server and client side. | 0.5
| Write the logic for saving and deleting from the server side. | 0.75
| Implement functionality to fetch and bind data from DB. | 0.5
| Testing And Error handleing | 0.25
Payment Item Button
Negative Prices
Cash In/Out
| Create UI design of Cash In/Out list. | 0.5
| Create a migration file to handle the database. | 0.25
| Bind & Populate data to the Cash In/Out. | 0.5
| Implement validation and error handling from server and client side. | 0.25
| Implement functionality to fetch and bind data from DB. | 0.25
| Testing And Error handleing | 0.25
| Extra Fee | 3.75
| Create UI design of extra Fee list. | 0.5
| Create a migration file to handle the database. | 0.5
| Bind & Populate data to the Extra Fees. | 0.5
| Write logic to automatically generate a new row when adding Extra Fees. | 0.5
| Write the logic, double-click the row, and then update the column value. | 0.5
| Implement validation and error handling from server and client side. | 0.25
| Write the logic for saving and deleting from the server side. | 0.5
| Implement functionality to fetch and bind data from DB. | 0.25
| Testing And Error handleing | 0.25